## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Public | All role | Show general introduction about bird clinic, reservation form, top services, top doctors, good feedback about bird's services, the system's specialities, and clinic's map | Phúc | Updated | iter1 | iter2
2 | User Login | Common | All role | Allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Ân | Done | iter2 | none
3 | Web Blogs List | Public | All role | Show the posts paginatedly (sorted by updated date, paginated) + the sider with the post search box, posts categories, static contacts/links; Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | Bách
4 | Web Blog Details | Public | All role | Show post details (including title, author, updated date, brief info, and post content) + the right sider with the post search box, post categories. The Blogs List page is shown when the user clicks on a post category | Bách
5 | Web Services List | Public | All role | List of services in the system: - Shown information for each service include: title, category, rated star, number of feedbacks, service fee and description - User can search by name; filter by speciality; sort by the fee or the name | Bách
6 | Web Service Details | Public | All role | View the details of the chosen service, including the introduction information (title, category, rated star, number of feedbacks, related services), overall description, and the reviews from patients (filtered by the rated star) | Bách
7 | User Register | Common | Guest | Allows the user to register to the system by inputing following information: full name, gender (Male, Female), email, mobile, user name, login password, confirm password; After that, user register for thier bird by input following information: Bird name, bird gender, breed, bird age, weight, ... User then needs to verify by clicking the link sent via email to him/her before being able to access the system | Ân | Doing | iter3 | none
8 | Forgot Password | Common | All role | The user to input his/her email to receive the reset password link - On clicking the link, the user is redirected to the page in which s/he input new password (twice) - Note that the link is only available for a specific time duration as configured in the system config file. | Ân
9 | Change Password | Common | All role | Allows the user to change his/her password by inputting his current password as well as new password (twice) | Ân
10 | User Profile | Common | All role | This is a pop-up screen which allows the user to view/edit his/her profile information, including the registered user information and the avatar image (s/he is not allowed to change the email) | Tuấn
11 | Bird's Profile | Customer | Customer | This is a pop-up screen which allows the user to view bird's information | Tuấn
12 | Edit bird's profile | Customer | Customer | allow customer to edit bird's infomation, such as 'name', "band no.", "weight",... *Cannot edit bird's "breed", "age" | Tuấn
13 | Create Reservation | Common | Customer/guest | 3 slide of booking form: Slide 1: user input personal info Slide 2: user input bird's info *Slide 1&2 can be skip if user was Customer Slide 3: user choose doctor & date => choose time slot => Send reservation | Tiến/Minh/Phúc
14 | Reservation list | Customer | Customer | Show the list of user's reservations paginatedly - Each reservation include below information: Reservation id, user's info, bird's info, reserved date, service, time to check up, total cost, reservation status; - On clicking the link under the reservation id, user would be redirected to the Reservation Information page *For customer role: they can only view their own reservations *For staff role: they can view all reservation that created by customers *For doctor role: they can only view their assigned and confirmed appointments | Tiến/Minh/Phúc
15 | Reservation detail | Customer | Customer/Staff/Doctor | Show the reservation details, including the information as below - The reservation id, reservation date, time to check up, total cost - Reservation status should be: "unconfirmed", "confirmed", "completed", "canceled" ( "unconfirmed" and "canceled" reservation will be delete after 5 days) (confirmed reservation would be consider as AN APPOINTMENT) - The receiver information: full name, gender, email, mobile - The bird information: name, type, age, gender, owner - The incharge doctor's information, - The bird medical record for that reservation. (The status must be "completed" & the doctor has updated ) *User view: - The button that allow the user to feedback. *Staff view: - The button that show the user's feedback detail. *Doctor view: - The button that allow doctor to add/edit medical record for the Completed appointment. For the submitted reservation, the user can choose to cancel the reservation | Tiến/Minh/Phúc
16 | View Bird's medical record | Customer | Customer | Show medical record for the selected reservation, including the information as below - Bird's info - Doctor's info - Doctor's diagnosis - Doctor's prescription - appointment date & time. | Tuấn/Phúc
17 | Create Feedback | Customer | Customer | Allow customer to feedback about the selected appointment. User will input the information as below: - Rating for the service. - feedback content. - pics and vids. | Tuấn/Phúc
18 | Cancel Reservation | Customer | Customer | Allow customer to cancel the selected reservation | Tiến/Minh/Phúc
19 | Update reservation | Staff | Staff/Doctor | *Staff update confirmation status. This function will notify the customer via email. *Doctor update status to "completed" | Tiến/Minh/Phúc
20 | Add medical record | Doctor | Doctor | Doctor add new medical record for the selected reservation, including: - Doctor's diagnosis - Doctor's prescription *system automatically add: Bird's info, Doctor's info, appointment date & time into the record. | Tuấn/Phúc
21 | Edit medical record | Doctor | Doctor | Doctor edit medical record for the selected reservation. Parts that doctor can edit: - Doctor's diagnosis - Doctor's prescription | Tuấn/Phúc
22 | feedback list | Staff | Staff | List of customer's feedback for each reservation, including: - Customer's name - Bird breed - Appointment date&time - Feedback title | Ân
23 | feedback detail | Staff | Staff | Show detail of the feedback, including: - Customer's info - Bird's info - Appointment Date&Time | Ân
24 | Create Blog | Staff | Staff | Allow staff add new blog by input these information: - Blog title - Category - Blog content - Blog reference | Bách
25 | Edit Blog | Staff | Staff | Allow Staff to edit posted blogs | Bách

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4